## Title
Multi Band Spectrum Award (MBSA2) The RurTel Transition Plan
| ComReg Document Number: | ComReg 23/39a
| Project Document Number: | MBSA2(23)013
| Date: | 3 May 2023
| Date Updated: | 17 April 2024
An Coimisiún um Rialáil Cumarsáide
Commission for Communications Regulation
1 Lárcheantar na nDugaí, Sráid na nGildeanna, BÁC 1, Éire, D01 E4X0.
One Dockland Central, Guild Street, Dublin 1, Ireland, D01 E4X0.
Teil ¦ Tel +353 1 804 9600 Suíomh ¦ Web www.comreg.ie

## Site Transition
Site Transition
Network Main Sites - Transition Milestones | [6 empty] | Transition Milestone |  | Progress Updates
Site Name | Eastings | Northings | Site Function | Network | Dependencies Subscribers | Dependencies Downstream Repeater Chain | Decommissioning Date | Note | March 2024
Letterkenny | 217007 | 411529 | Hub | North Donegal | n/a | Mongorry, Ashdevlin, Barnesmore, Evishbride (aka Evisbreedy), Ballinahinch (aka Ballinacrick), Ballyhark N (aka Ballyheerin) | Q4 2024 | Eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
Mongorry | 223500 | 404800 | Repeater | North Donegal | See 'Subscriber Transition Tab' | Ashdevlin, Barnesmore, Evishbride (aka Evisbreedy), Ballinahinch (aka Ballinacrick), Ballyhark N (aka Ballyheerin) | Q4 2024 | Eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
Ashdevlin | 239200 | 426000 | Repeater | North Donegal | See 'Subscriber Transition Tab' | Evishbride (aka Evisbreedy), Ballinahinch (aka Ballinacrick), Ballyhark N (aka Ballyheerin) | Q4 2024 | Eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
Barnesmore | 203700 | 385300 | Repeater | North Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q4 2024 | eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
Evishbride (aka Evisbreedy) | 243130 | 434816 | Repeater | North Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q1 2024 |  | Decommissioned
Ballinahinch (aka Ballinacrick) | 222021 | 446011 | Repeater | North Donegal | n/a | Ballyhark N (aka Ballyheerin) | Q4 2024 | Eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
Ballyhark N (aka Ballyheerin) | 217608 | 441013 | Repeater | North Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q4 2024 | Eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
Mulmosog | 174600 | 387100 | Hub | South Donegal | See 'Subscriber Transition Tab' | St Johns (aka Ballysaggart), Boulty Patrick, Lough muilt, Tullybeg, Dungloe Test Site, Maghera, Leamagowra, Maum | Q4 2024 | Eir has yet to identify an alternative service solution to migrate subscriber/s served downstream of this site. Therefore, the decommissioning date for this site is noted as provisional and will be kept under review as this Transition Plan progresses. | New decommissioning date – Q4 2024
St Johns (aka Ballysaggart) | 172899 | 371511 | Repeater | South Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q1 2024 |  | Decommissioned
Boulty Patrick | 195500 | 398700 | Repeater | South Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q4 2024 |  | New decommissioning date – Q4 2024
Lough muilt | 176300 | 380200 | Repeater | South Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q4 2024 |  | New decommissioning date – Q4 2024
Tullybeg | 175700 | 394900 | Repeater | South Donegal | See 'Subscriber Transition Tab' | Maghera, Leamagowra, Maum | Q4 2024 |  | New decommissioning date – Q4 2024
Dungloe Test Site | 176795 | 411807 | Test Site | South Donegal | n/a | n/a (end of chain) | Q1 2024 |  | Decommissioned
Maghera | 163719 | 388930 | Repeater | South Donegal | See 'Subscriber Transition Tab' | Leamagowra, Maum | Q4 2024 |  | New decommissioning date – Q4 2024
Leamagowra | 167400 | 386300 | Repeater | South Donegal | See 'Subscriber Transition Tab' | Maum | Q4 2024 |  | New decommissioning date – Q4 2024
Maum | 166738 | 388405 | Repeater | South Donegal | See 'Subscriber Transition Tab' | n/a (end of repeater chain) | Q4 2024 |  | New decommissioning date – Q4 2024

## Subscriber Transition
Site for Subscriber Connection | cct_no | cust_name | cust_add | Eircode | Easting | Northing | Substation | Transition status at Date of Adoption of this Transition Plan | Availability of Alternative Platform at Customer Premises (see Key below) | Date for Subscriber’s migration from RurTel | Other relevant details | July 2023 | December 2023 | March 2024
Barnsemore | [6 empty] | Treetops (SST) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Mobile coverage available | Engaging with retail provider | Service no longer required | Service no longer required
Barnsemore | [6 empty] | S23 Cark (Letterkenny) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Eir has yet to identify an alternative service solution to migrate this subscriber from RurTel. Therefore, the Transition milestone date for this subscriber’s migration is noted as provisional and will be kept under review as this Transition Plan progresses. | No update | Service no longer required | Service no longer required
Boulty Patrick | [6 empty] | S99 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - [ "Redacted" ] | Site proceeding to build | Site build ongoing
Tullybeg | [6 empty] | Tullybeg Repeater | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Mobile coverage available | Ceased | Ceased | Ceased
Boulty Patrick | [6 empty] | S99 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - ["Redacted "] | Site proceeding to build | Site build ongoing
Boulty Patrick | [6 empty] | S99 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - [ "Redacted "] | Site proceeding to build | Site build ongoing
Boulty Patrick | [6 empty] | S99 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - [" Redacted "] | Site proceeding to build | Site build ongoing
Muam | [6 empty] | S38 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Marco site to provide Mobile coverage to this customer - [" Redacted "] | Site proceeding to build | Site build ongoing
Leamagowra | [6 empty] | S33 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - [ " Redacted "] | Site proceeding to build | Site build ongoing
Barnsemore | [6 empty] | Barnesmore Repeater (RST) on Letterkenny CST. | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Mobile coverage available | Ceased | Ceased | Ceased
Lough Muilt | [6 empty] | S29 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - ["Redacted "] | Site proceeding to build | Service no longer required
St. Johns – Ballysaggart | [6 empty] | S36 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Mobile coverage check in planning | Retesting to take place at this location. Very remote, alternative solution may be required. | Migrated | Ceased
Lough Muilt | [6 empty] | S30 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - [ " Redacted "] | Site proceeding to build | Site build ongoing
Barnsemore | [6 empty] | Barnse7 (Letterkenny) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Eir has yet to identify an alternative service solution to migrate this subscriber from RurTel. Therefore, the Transition milestone date for this subscriber’s migration is noted as provisional and will be kept under review as this Transition Plan progresses. | Retesting to take place at this location. Very remote, alternative solution may be required. | Engaging with retail provider | Engaging with retail provider
Mongorry | [6 empty] | S11 (Letterkenny) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Mobile coverage available | Order requested - raised in March | Migrated | Ceased
Ballyheerin (Ballyhark N) | [6 empty] | Glassan SST (Letterkenny) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Eir has yet to identify an alternative service solution to migrate this subscriber from RurTel. Therefore, the Transition milestone date for this subscriber’s migration is noted as provisional and will be kept under review as this Transition Plan progresses. | Retesting to take place at this location. New site ["Redacted "] brought on-air in March may provide the required mobile signal. | Retest complete. Good mobile coverage. Next step to engage retail provider | Engaging with retail provider
Evishbride (Evisbreedy) | [6 empty] | S5 (Letterkenny) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 | Mobile coverage check in planning | Retesting to take place at this location. Very remote, alternative solution may be required. | Retest complete. Good mobile coverage. Next step to engage retail provider | Ceased
Ashdevlin | [6 empty] | S74 (Letterkenny) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Mobile coverage check in planning | Retesting to take place at this location. Very remote, alternative solution may be required. | Retest complete. Good mobile coverage. Next step to engage retail provider | Engaging with retail provider
Mulmosog | [6 empty] | S23 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2023 (Provisional Date) | Eir has yet to identify an alternative service solution to migrate this subscriber from RurTel. Therefore, the Transition milestone date for this subscriber’s migration is noted as provisional and will be kept under review as this Transition Plan progresses. | Retesting to take place at this location. New site ["Redacted "]brought on-air in March may provide the required mobile signal. | Retest complete. Good mobile coverage. Next step to engage retail provider | Ceased
Mulmosog | [6 empty] | S23 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Eir has yet to identify an alternative service solution to migrate this subscriber from RurTel. Therefore, the Transition milestone date for this subscriber’s migration is noted as provisional and will be kept under review as this Transition Plan progresses. | Retesting to take place at this location. New site ["Redacted "] brought on-air in March may provide the required mobile signal. | Retest complete. Good mobile coverage. Next step to engage retail provider | FCS migration ongoing
Maghera | [6 empty] | S66 (Dungloe) | Actively pursuing a transistion strategy for this customer | Option 1 : Mobile Option 2 : FMS Option 3 : FCS | Q4 2024 | Repeater solution under investigation | Plan to rollout a Mobile Macro site to provide Mobile coverage to this customer - [ "Redacted "] | Site proceeding to build | Site build ongoing

## Reporting Method
Reporting Method
(1) Eir will provide progress updates to ComReg in relation to the RurTel Transition Plan in line with the timeframes identified in Table 1 below.
Table 1: Dates for progress updates
2023 | End of July, End of November
2024 | End of March, or earlier if Transition Activites have been completed earlier
After March 2024 (in the event of delay to completion of the Transition Activities) | End of March, End of July and End of November each year where relevant
(2) The updates should (i) outline progress made and (ii) identify any updates to the RurTel Transition Plan (e.g. for RurTel subscribers migrated, RurTel sites decommissioned, changes in the migration/decommissioning dates, changes in the Transition status of subscribers etc.)
(3) The updates should be provided via email to ComReg. Details of relevant contacts for the reporting in ComReg and Eir are set out in Table 2 below.
(4) ComReg and Eir will notify one another of any changes to the contacts set out in Table 2, as soon as appropriate.
Table 2: Email contact details for progress updates on the RurTel Transition Plan
ComReg | Martin.ODonoghue@comreg.ie
cc: joseph.coughlan@comreg.ie
cc: pat.mcmahon@comreg.ie
Eir